## Migration Inventory
Workspace Name | Capacity Name | SKU | Source Region | Target Region | Item Name | Item Type | Movable? | Migration Complexity | Suggested Wave | Business Owner | Data Size (GB) | External Dependencies | Notes
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | lh_sm_data | Lakehouse | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1 | Healthcaredatasolution | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_admin | Lakehouse | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_environment | Environment | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_bronze | Lakehouse | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_silver | Lakehouse | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_config_notebook | Notebook | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_bronze_silver_flatten | Notebook | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_raw_process_movement | Notebook | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_fhir_flattening_sample | Notebook | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_generic_dtt_transformation | Notebook | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_fhir_ndjson_bronze_ingestion | Notebook | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_clinical_data_foundation_ingestion | DataPipeline | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_sdoh_bronze_silver_flatten | Notebook | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_sdoh_raw_extract_bronze_ingestion | Notebook | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_sdoh_ingestion | DataPipeline | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_ai_enrichments_metadatastore | Lakehouse | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_ai_enrichments_bronze_ingestion | Notebook | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_ai_enrichments_silver_ingestion | Notebook | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_ai_enrichments_ta4h_execution | Notebook | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_ai_enrichments_medimage_parse_execution | Notebook | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_ai_enrichments_medimage_insight_execution | Notebook | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_ai_enrichments_ingestion | DataPipeline | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | lh_sm_data_notebook_01 | Notebook | ❌ Non-Movable | High | 3
ws-powerapps-demo | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | lh_powerapps_demo | Lakehouse | ❌ Non-Movable | High | 3
ws-powerapps-demo | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | mirror-powerappsdb | MirroredDatabase | ❌ Non-Movable | High | 3
ws-powerapps-demo | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | fabric-warehouse-lakehouse-metrics-old | Notebook | ❌ Non-Movable | High | 3
ws-powerapps-demo | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | fabric-warehouse-lakehouse-metrics_old3 | Notebook | ❌ Non-Movable | High | 3
ws-powerapps-demo | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | fabric-warehouse-lakehouse-metrics | Notebook | ❌ Non-Movable | High | 3
ws-powerapps-demo | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | OneLakeSorageSize | Notebook | ❌ Non-Movable | High | 3
ws-powerapps-demo | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | fabric-spark-monitoring-setup | Notebook | ❌ Non-Movable | High | 3
ws-powerapps-demo | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | fabric-warehouse-performance-softdelete | Notebook | ❌ Non-Movable | High | 3
ws-powerapps-demo | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | fabric-notebook-pipeline-efficiency | Notebook | ❌ Non-Movable | High | 3
ws-powerapps-demo | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | fabric-capacity-migration-inventory-1 | Notebook | ❌ Non-Movable | High | 3
ws-powerapps-demo | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | lh_fabric_inventory | Lakehouse | ❌ Non-Movable | High | 3
ws-powerapps-demo | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | lh_fabric_inventory | SQLEndpoint | ❌ Non-Movable | High | 3
ws-powerapps-demo | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | mirror-powerappsdb | SQLEndpoint | ❌ Non-Movable | High | 3
ws-powerapps-demo | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | dw-powerapps-demo | Warehouse | ❌ Non-Movable | High | 3
ws-powerapps-demo | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | lh_powerapps_demo | SQLEndpoint | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_ai_enrichments_metadatastore | SQLEndpoint | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_silver | SQLEndpoint | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_bronze | SQLEndpoint | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | healthcare1_msft_admin | SQLEndpoint | ❌ Non-Movable | High | 3
ng_poc_01 | ngfabricf2westus3001 | F4 | West US 3 | East US 2 | lh_sm_data | SQLEndpoint | ❌ Non-Movable | High | 3

## Migration Phases
Phase | Phase Name | Key Milestone | Owner | Planned Start | Planned End | Actual Start | Actual End | Status | % Complete | Dependencies | Notes
Phase 0 | Discovery & Inventory | Inventory complete & business sign-off |  | 2026-03-06 | 2026-03-20 |  |  | Not Started | 0% | Admin API access | Run this notebook
Phase 1 | Target Capacity Setup in East US 2 | Capacity provisioned in East US 2 |  | 2026-03-20 | 2026-03-27 |  |  | Not Started | 0% | Azure subscription | Match SKU; configure networking
Phase 2 | Wave 1 – Low Complexity | Movable-only workspaces migrated |  | 2026-03-27 | 2026-04-10 |  |  | Not Started | 0% | Phase 1 | Reports, Dashboards, Semantic models
Phase 3 | Wave 2 – Medium Complexity | Lakehouses/Warehouses migrated with data |  | 2026-04-10 | 2026-05-01 |  |  | Not Started | 0% | Phase 2 | AzCopy/Copy Job for data
Phase 4 | Wave 3 – High Complexity | Notebooks, Pipelines recreated & validated |  | 2026-05-01 | 2026-05-29 |  |  | Not Started | 0% | Phase 3 | Git integration for definitions
Phase 5 | Validation & Decommission | Business sign-off, source decommissioned |  | 2026-05-29 | 2026-06-12 |  |  | Not Started | 0% | All phases | Parallel run → cutover → decom

## Risk Register
Risk ID | Risk Description | Category | Likelihood | Impact | Risk Level | Mitigation Strategy | Risk Owner | Status | Notes
R-001 | Non-movable items block workspace reassignment | Technical | High | High | Critical | Pre-inventory all items; remove non-movable before reassignment |  | Open
R-002 | Dataflow Gen2 staging lakehouses block migration | Technical | Medium | High | High | Delete Dataflow Gen2 items first, then staging lakehouses |  | Open
R-003 | Admin API rate limits (200 req/hr) slow discovery | Technical | Medium | Low | Medium | Retry/backoff built into notebook helper |  | Mitigated
R-004 | Large-storage semantic models cannot cross regions | Technical | Medium | High | High | Identify large-storage models early; switch or recreate |  | Open
R-005 | Data loss during Lakehouse/Warehouse migration | Data | Low | Critical | High | Full backup; validate row counts and checksums post-copy |  | Open
R-006 | Running jobs cancelled during reassignment | Operational | High | Medium | High | Schedule during maintenance windows; notify users |  | Open
R-007 | VNet gateways region-bound – need new provisioning | Networking | Medium | High | High | Provision new VNet + gateway in target region before migration |  | Open
R-008 | Gateway-bound connections break after migration | Integration | Medium | High | High | Catalog gateway connections; recreate on target gateways |  | Open
R-009 | Private Link breaks after migration | Networking | Medium | High | High | Disable Private Link before migration; reconfigure after |  | Open
R-010 | Insufficient permissions to run inventory | Access | Medium | High | High | Run permission pre-flight check; request Fabric Admin role |  | Open

## RACI Matrix
Task / Activity | Fabric Admin | Cloud Platform | Data Engineering | BI / Analytics | Business Owner | Security / Network | Project Manager
Run inventory notebook | R/A | I | C | I | I | I | I
Provision target capacity | R | A | I | I | I | C | I
Configure networking (VNet/PE) | C | R/A | I | I | I | R | I
Provision VNet gateways in target | R | A | I | I | I | C | I
Backup lakehouse/warehouse data | C | I | R/A | I | I | I | I
Migrate Wave 1 (movable only) | R/A | I | I | C | I | I | I
Copy data to target lakehouses | C | I | R/A | I | I | I | I
Remove non-movable items | R/A | I | C | C | I | I | I
Reassign workspaces | R/A | I | I | I | I | I | I
Recreate pipelines & notebooks | C | I | R/A | I | I | I | I
Re-bind gateway connections | R | C | C | I | I | I | I
Validate reports & dashboards | I | I | I | R/A | C | I | I
Business sign-off per wave | I | I | I | C | R/A | I | I
Decommission source capacities | R | A | I | I | I | C | I
Overall project coordination | C | C | C | C | C | C | R/A

## Issue Tracker
Issue ID | Date Raised | Workspace / Item | Issue Description | Severity (P1-P4) | Assigned To | Status | Resolution | Date Resolved | Notes
ISS-001 |  | (Example) | (Example issue) | P2 |  | Open

## Validation Checklist
Wave | Workspace Name | Validation Step | Expected Result | Actual Result | Pass/Fail | Validated By | Date | Notes
1 | (Wave 1 WS) | Reports render correctly | All visuals load
1 | (Wave 1 WS) | Semantic model refresh succeeds | Refresh < 2x baseline
1 | (Wave 1 WS) | Dashboard tiles load | All tiles display data
2 | (Wave 2 WS) | Lakehouse row counts match | Row count delta = 0
2 | (Wave 2 WS) | Warehouse query results match | Checksum passes
2 | (Wave 2 WS) | Semantic models connect to new lakehouse | No errors
3 | (Wave 3 WS) | Notebooks execute without error | All cells pass
3 | (Wave 3 WS) | Pipelines run end-to-end | Expected output
3 | (Wave 3 WS) | Gateway connections functional | Data flows via new gateway
All | ALL | Capacity utilization < 80% | CU% < 80%
All | ALL | No orphaned items in source | Source capacity empty